## Master Control Table
0 | Description of Item | Country of Origin | Unit of Measur ement | Quantity | kisu | USD | USD% | Taka | BDT% | Equivelent USD | Weight of the Project (%) | Design | Procurement | Logistics | Construction | Installation, Testing & Commissioning | Financial
Weight of Each Type of Work | [10 empty] | 100% | 10% | 15% | 10% | 20% | 15% | 30%
Equipment Supply
1 | 33kV GIS | EU | Set | 1 | 0.29 | 0.29 | 29 | 0.0232 | 2.32 | 0.29029 | 28.67% | 28.67% | 28.67% | 28.67% | 28.67% | 28.67% | 28.67%
2 | 11kV GIS | EU | Set | 1 | 0.27 | 0.27 | 27 | 0.0216 | 2.16 | 0.27027 | 26.69% | 26.69% | 26.69% | 26.69% | 26.69% | 26.69% | 26.69%
3 | Power Transformer (33/11 kV, 20/26 MVA) | China | Nos | 1 | 0.03 | 0.03 | 3 | 0.0024 | 0.24 | 0.03003 | 2.966% | 2.966% | 2.966% | 2.966% | 2.966% | 2.966% | 2.966%
4 | Station Transformer (33/0.4 kV, 200 kVA) | China | Nos | 2 |  | 0.01 | 1 | 0.0008 | 0.08 | 0.01001 | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886%
5 | AC Distribution Panel | China | Set | 2 |  | 0.015 | 1.5 | 0.0012 | 0.12 | 0.015015 | 1.483% | 1.483% | 1.483% | 1.483% | 1.483% | 1.483% | 1.483%
6 | DC Distribution Panel | China | Set | 2 |  | 0.015 | 1.5 | 0.0012 | 0.12 | 0.015015 | 1.483% | 1.483% | 1.483% | 1.483% | 1.483% | 1.483% | 1.483%
7 | Battery and Battery Charger (110V) | China | Set | 1 |  | 0.02 | 2 | 0.0016 | 0.16 | 0.02002 | 1.977% | 1.977% | 1.977% | 1.977% | 1.977% | 1.977% | 1.977%
8 | XLPE Cable (33kV, 1x500sq.mm) | China | Lot | 1 |  | 0.03 | 3 | 0.0024 | 0.24 | 0.03003 | 2.966% | 2.966% | 2.966% | 2.966% | 2.966% | 2.966% | 2.966%
9 | XLPE Cable (11kV, 2x500sq.mm) and (2x120sq.mm) | China | Lot | 1 |  | 0.025 | 2.5 | 0.002 | 0.2 | 0.025025 | 2.472% | 2.472% | 2.472% | 2.472% | 2.472% | 2.472% | 2.472%
10 | XLPE Cable (11kV, 3Cx95sq.mm) | China | Lot | 1 |  | 0.014 | 1.4 | 0.00112 | 0.112 | 0.014014 | 1.384% | 1.384% | 1.384% | 1.384% | 1.384% | 1.384% | 1.384%
11 | XLPE Cable (11kV, 3Cx185sq.mm) | China | Lot | 1 |  | 0.017 | 1.7 | 0.00136 | 0.136 | 0.017017 | 1.681% | 1.681% | 1.681% | 1.681% | 1.681% | 1.681% | 1.681%
12 | Cable Termination (33kV, 11kV, 0.415kV) | China | Lot | 1 |  | 0.06 | 6 | 0.0048 | 0.48 | 0.06006 | 5.932% | 5.932% | 5.932% | 5.932% | 5.932% | 5.932% | 5.932%
13 | Control Cable and LV Power Cables | China | Sets | 1 |  | 0.014 | 1.4 | 0.00112 | 0.112 | 0.014014 | 1.384% | 1.384% | 1.384% | 1.384% | 1.384% | 1.384% | 1.384%
14 | Groundingas Materials Including Cable/Conductor | China | Sets | 12 |  | 0.003 | 0.3 | 0.00024 | 0.024 | 0.003003 | 0.2966% | 0.2966% | 0.2966% | 0.2966% | 0.2966% | 0.2966% | 0.2966%
15 | Surge Arrester (Station type 33 kV) | China | Sets | 4 |  | 0.0077 | 0.77 | 0.000616 | 0.0616 | 0.0077077 | 0.7613% | 0.7613% | 0.7613% | 0.7613% | 0.7613% | 0.7613% | 0.7613%
16 | Surge Arrester (Station type 33 kV) | China | Lot | 1 |  | 0.0023 | 0.23 | 0.000184 | 0.0184 | 0.0023023 | 0.2274% | 0.2274% | 0.2274% | 0.2274% | 0.2274% | 0.2274% | 0.2274%
17 | Air Conditioner of 48,000 BTU Split Type and Exhaust Fan | China | Sets | 4 |  | 0.0045 | 0.45 | 0.00036 | 0.036 | 0.0045045 | 0.4449% | 0.4449% | 0.4449% | 0.4449% | 0.4449% | 0.4449% | 0.4449%
18 | Lighting & Electrification (Outdoor & Indoor) | China | Lot | 1 |  | 0.0055 | 0.55 | 0.00044 | 0.044 | 0.0055055 | 0.5438% | 0.5438% | 0.5438% | 0.5438% | 0.5438% | 0.5438% | 0.5438%
19 | Steel Supporting Structures of Equipment | China | Lot | 1 |  | 0.01 | 1 | 0.0008 | 0.08 | 0.01001 | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886%
20 | Fire Fighting Equipment | China | Set | 6 |  | 0.008 | 0.8 | 0.00064 | 0.064 | 0.008008 | 0.7909% | 0.7909% | 0.7909% | 0.7909% | 0.7909% | 0.7909% | 0.7909%
21 | LV MCCB Pane | China | Nos. | 2 |  | 0.006 | 0.6 | 0.00048 | 0.048 | 0.006006 | 0.5932% | 0.5932% | 0.5932% | 0.5932% | 0.5932% | 0.5932% | 0.5932%
22 | Substation Automation system | EU | Lot | 1 |  | 0.09 | 9 | 0.0072 | 0.72 | 0.09009 | 8.898% | 8.898% | 8.898% | 8.898% | 8.898% | 8.898% | 8.898%
23 | LED TV, Laptop, Scanner, Printer, LED Electronic Sign Board, Furniture for control room Elivator | China | Lot | 1 |  | 0.003 | 0.3 | 0.00024 | 0.024 | 0.003003 | 0.2966% | 0.2966% | 0.2966% | 0.2966% | 0.2966% | 0.2966% | 0.2966%
24 | Recommended Spare parts for GIS Substation | EU | L.S | 1 |  | 0.01 | 1 | 0.0008 | 0.08 | 0.01001 | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886%
25 | Isolator (11kV, Outdoor Type) | EU | Set | 12 |  | 0.03 | 3 | 0.0024 | 0.24 | 0.03003 | 2.966% | 2.966% | 2.966% | 2.966% | 2.966% | 2.966% | 2.966%
26 | Balance of the system |  | Lot | 1 |  | 0.01 | 1 | 0.0008 | 0.08 | 0.01001 | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886% | 0.9886%
Civil Works | [6 empty] | 0
27 | Land Development with Filling by Sand. | BD | m³ | 3000 |  |  | 0 | 9.2% | 9.2 | 0.00115 | 0.1136% | 0.1136% | 0.1136% | 0.1136% | 0.1136% | 0.1136% | 0.1136%
28 | Sub-Station Buliding | BD | Sq.m. | 1400 |  |  | 0 | 25.16% | 25.16 | 0.003145 | 0.3106% | 0.3106% | 0.3106% | 0.3106% | 0.3106% | 0.3106% | 0.3106%
29 | Transformer Room | BD |  |  |  |  | 0 | 3.49% | 3.49 | 0.00043625 | 0.04309% | 0.04309% | 0.04309% | 0.04309% | 0.04309% | 0.04309% | 0.04309%
30 | Switchgear Room | BD |  |  |  |  | 0 | 2.79% | 2.79 | 0.00034875 | 0.03444% | 0.03444% | 0.03444% | 0.03444% | 0.03444% | 0.03444% | 0.03444%
31 | Control Room | BD |  |  |  |  | 0 | 2.13% | 2.13 | 0.00026625 | 0.0263% | 0.0263% | 0.0263% | 0.0263% | 0.0263% | 0.0263% | 0.0263%
32 | Office Room | BD |  |  |  |  | 0 | 1.39% | 1.39 | 0.00017375 | 0.01716% | 0.01716% | 0.01716% | 0.01716% | 0.01716% | 0.01716% | 0.01716%
33 | Boundary Wall / Retain wall | BD | Rm | 275 |  |  | 0 | 2.57% | 2.57 | 0.00032125 | 0.03173% | 0.03173% | 0.03173% | 0.03173% | 0.03173% | 0.03173% | 0.03173%
34 | Sub-Station Entrance Gate | BD |  |  |  |  | 0 | 0.18% | 0.18 | 2.25e-05 | 0.002222% | 0.002222% | 0.002222% | 0.002222% | 0.002222% | 0.002222% | 0.002222%
35 | Guard post | BD |  |  |  |  | 0 | 0.18% | 0.18 | 2.25e-05 | 0.002222% | 0.002222% | 0.002222% | 0.002222% | 0.002222% | 0.002222% | 0.002222%
36 | Drainage System | BD |  |  |  |  | 0 | 0.75% | 0.75 | 9.375e-05 | 0.009259% | 0.009259% | 0.009259% | 0.009259% | 0.009259% | 0.009259% | 0.009259%
37 | Inside Road, Approach Road, Walkway | BD | Rm | 138 |  |  | 0 | 6.44% | 6.44 | 0.000805 | 0.07951% | 0.07951% | 0.07951% | 0.07951% | 0.07951% | 0.07951% | 0.07951%
38 | Leveling, Landscaping, Tree plantation, Gardening and beautification etc | BD | LS | 1 |  |  | 0 | 5.06% | 5.06 | 0.0006325 | 0.06247% | 0.06247% | 0.06247% | 0.06247% | 0.06247% | 0.06247% | 0.06247%
39 | Yard lighting and emergency lighting | BD | LS | 1 |  |  | 0 | 4.6% | 4.6 | 0.000575 | 0.05679% | 0.05679% | 0.05679% | 0.05679% | 0.05679% | 0.05679% | 0.05679%
40 | Installation including Testing, commissioning | China | Set | 1 |  |  | 0 | 12.7% | 12.7 | 0.0015875 | 0.1568% | 0.1568% | 0.1568% | 0.1568% | 0.1568% | 0.1568% | 0.1568%
41 | Inspection & Traning | China |  |  |  |  | 0 | 8.46% | 8.46 | 0.0010575 | 0.1044% | 0.1044% | 0.1044% | 0.1044% | 0.1044% | 0.1044% | 0.1044%
42 | Electrical Drawing | China | Lot | 1 |  |  | 0 | 4.14% | 4.14 | 0.0005175 | 0.05111% | 0.05111% | 0.05111% | 0.05111% | 0.05111% | 0.05111% | 0.05111%
43 | Civil Drawing | BD | Lot | 1 |  |  | 0 | 1.84% | 1.84 | 0.00023 | 0.02272% | 0.02272% | 0.02272% | 0.02272% | 0.02272% | 0.02272% | 0.02272%
44 | Balance of the system | BD | Lot | 1 |  |  | 0 | 0.92% | 0.92 | 0.000115 | 0.01136% | 0.01136% | 0.01136% | 0.01136% | 0.01136% | 0.01136% | 0.01136%
[6 empty] | 1 |  | 1 |  | 1.0125 | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Exchange Rate of USD to Taka on 02nd January, 2018 |  | 80
Total Contract Price | [5 empty] | 1 |  | 1 |  | 1.0125
[7 empty] | 100 |  | 100

## Design
Sl.No. | Description of Item | Country of Origin | Unit of Measur ement | Quantity | Weight of the work (%) | Design
Equipment Supply | [5 empty] | Submit to PD office | Forward to Design Department Three | Forward to PD office | Forward to Design Department Two | Forward to PD office | Receive Approved Drawing from PD Office | Handover Approved Drawing to Site Engineer | Remarks
1 | 33kV GIS | EU | Set | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
2 | 11kV GIS | EU | Set | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
3 | Power Transformer (33/11 kV, 20/26 MVA) | China | Nos | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
4 | Station Transformer (33/0.4 kV, 200 kVA) | China | Nos | 2 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
5 | AC Distribution Panel | China | Set | 2 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
6 | DC Distribution Panel | China | Set | 2 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
7 | Battery and Battery Charger (110V) | China | Set | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
8 | XLPE Cable (33kV, 1x500sq.mm) | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
9 | XLPE Cable (11kV, 2x500sq.mm) and (2x120sq.mm) | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
10 | XLPE Cable (11kV, 3Cx95sq.mm) | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
11 | XLPE Cable (11kV, 3Cx185sq.mm) | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
12 | Cable Termination (33kV, 11kV, 0.415kV) | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
13 | Control Cable and LV Power Cables | China | Sets | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
14 | Groundingas Materials Including Cable/Conductor | China | Sets | 12 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
15 | Surge Arrester (Station type 33 kV) | China | Sets | 4 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
16 | Surge Arrester (Station type 11 kV) | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
17 | Air Conditioner of 48,000 BTU Split Type and Exhaust Fan | China | Sets | 4 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
18 | Lighting & Electrification (Outdoor & Indoor) | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
19 | Steel Supporting Structures of Equipment | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
20 | Fire Fighting Equipment | China | Set | 6 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
21 | LV MCCB Pane | China | Nos. | 2 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
22 | Substation Automation system | EU | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
23 | LED TV, Laptop, Scanner, Printer, LED Electronic Sign Board, Furniture for control room Elivator | China | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
24 | Recommended Spare parts for GIS Substation | EU | L.S | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
25 | Isolator (11kV, Outdoor Type) | EU | Set | 12 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
26 | Balance of the system |  | Lot | 1 | 100% | 50% |  |  | 10% | 30% | 5% | 5%
Civil Works
27 | Land Development with Filling by Sand. | BD | m³ | 3000 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
28 | Sub-Station Buliding | BD | Sq.m. | 1400 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
29 | Transformer Room | BD |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
30 | Switchgear Room | BD |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
31 | Control Room | BD |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
32 | Office Room | BD |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
33 | Boundary Wall / Retain wall | BD | Rm | 275 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
34 | Sub-Station Entrance Gate | BD |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
35 | Guard post | BD |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
36 | Drainage System | BD |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
37 | Inside Road, Approach Road, Walkway | BD | Rm | 138 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
38 | Leveling, Landscaping, Tree plantation, Gardening and beautification etc | BD | LS | 1 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
39 | Yard lighting and emergency lighting | BD | LS | 1 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
40 | Installation including Testing, commissioning | China | Set | 1 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
41 | Inspection & Traning | China |  |  | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
42 | Electrical Drawing | China | Lot | 1 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
43 | Civil Drawing | BD | Lot | 1 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
44 | Balance of the system | BD | Lot | 1 | 100% | 50% | 7% | 20% | 5% | 8% | 5% | 5%
Total Weight of the Design Work |  |  |  |  | 100%

## Sheet1 (hidden)
a | 23 | a | 23
|  | x | 45
|  | b | 56
|  | c | 67
|  | d | 78

## Procurement
Sl.No. | Description of Item | Country of Origin | Unit of Measur ement | Quantity | Weight of the work (%) | Procurement
Equipment Supply | [5 empty] | Call for Offer | Collect Offer | Contract Sign with Supplier | Take out Goods from Manufacturer | Collect Shipping Documents | Handover Shipping Documents to Logistics Department | Remarks
1 | 33kV GIS | EU | Set | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
2 | 11kV GIS | EU | Set | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
3 | Power Transformer (33/11 kV, 20/26 MVA) | China | Nos | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
4 | Station Transformer (33/0.4 kV, 200 kVA) | China | Nos | 2 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
5 | AC Distribution Panel | China | Set | 2 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
6 | DC Distribution Panel | China | Set | 2 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
7 | Battery and Battery Charger (110V) | China | Set | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
8 | XLPE Cable (33kV, 1x500sq.mm) | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
9 | XLPE Cable (11kV, 2x500sq.mm) and (2x120sq.mm) | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
10 | XLPE Cable (11kV, 3Cx95sq.mm) | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
11 | XLPE Cable (11kV, 3Cx185sq.mm) | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
12 | Cable Termination (33kV, 11kV, 0.415kV) | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
13 | Control Cable and LV Power Cables | China | Sets | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
14 | Groundingas Materials Including Cable/Conductor | China | Sets | 12 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
15 | Surge Arrester (Station type 33 kV) | China | Sets | 4 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
16 | Surge Arrester (Station type 11 kV) | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
17 | Air Conditioner of 48,000 BTU Split Type and Exhaust Fan | China | Sets | 4 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
18 | Lighting & Electrification (Outdoor & Indoor) | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
19 | Steel Supporting Structures of Equipment | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
20 | Fire Fighting Equipment | China | Set | 6 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
21 | LV MCCB Pane | China | Nos. | 2 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
22 | Substation Automation system | EU | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
23 | LED TV, Laptop, Scanner, Printer, LED Electronic Sign Board, Furniture for control room Elivator | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
24 | Recommended Spare parts for GIS Substation | EU | L.S | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
25 | Isolator (11kV, Outdoor Type) | EU | Set | 12 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
26 | Balance of the system |  | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
Civil Works
27 | Land Development with Filling by Sand. | BD | m³ | 3000 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
28 | Sub-Station Buliding | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
29 | Transformer Room | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
30 | Switchgear Room | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
31 | Control Room | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
32 | Office Room | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
33 | Boundary Wall / Retain wall | BD | Rm | 275 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
34 | Sub-Station Entrance Gate | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
35 | Guard post | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
36 | Drainage System | BD |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
37 | Inside Road, Approach Road, Walkway | BD | Rm | 138 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
38 | Leveling, Landscaping, Tree plantation, Gardening and beautification etc | BD | LS | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
39 | Yard lighting and emergency lighting | BD | LS | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
40 | Installation including Testing, commissioning | China | Set | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
41 | Inspection & Traning | China |  |  | 100% | 10% | 10% | 15% | 50% | 10% | 5%
42 | Electrical Drawing | China | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
43 | Civil Drawing | BD | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
44 | Balance of the system | BD | Lot | 1 | 100% | 10% | 10% | 15% | 50% | 10% | 5%
Total Weight of the Procurement Work |  |  |  |  | 100%

## Logistics
Sl.No. | Description of Item | Country of Origin | Unit of Measur ement | Quantity | Weight of the work (%) | Logistics
Equipment Supply | [5 empty] | Submit Shipping Documents to Presenting Bank | Collect Shipping Documents from Issuing Bank | Endorsement Shipping Documents | Submit to Customs Office | Take Out Goods from Port | Send to Site | Handover Shipping Documents to Finance Department | Remarks
1 | 33kV GIS | EU | Set | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
2 | 11kV GIS | EU | Set | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
3 | Power Transformer (33/11 kV, 20/26 MVA) | China | Nos | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
4 | Station Transformer (33/0.4 kV, 200 kVA) | China | Nos | 2 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
5 | AC Distribution Panel | China | Set | 2 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
6 | DC Distribution Panel | China | Set | 2 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
7 | Battery and Battery Charger (110V) | China | Set | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
8 | XLPE Cable (33kV, 1x500sq.mm) | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
9 | XLPE Cable (11kV, 2x500sq.mm) and (2x120sq.mm) | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
10 | XLPE Cable (11kV, 3Cx95sq.mm) | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
11 | XLPE Cable (11kV, 3Cx185sq.mm) | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
12 | Cable Termination (33kV, 11kV, 0.415kV) | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
13 | Control Cable and LV Power Cables | China | Sets | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
14 | Groundingas Materials Including Cable/Conductor | China | Sets | 12 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
15 | Surge Arrester (Station type 33 kV) | China | Sets | 4 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
16 | Surge Arrester (Station type 11 kV) | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
17 | Air Conditioner of 48,000 BTU Split Type and Exhaust Fan | China | Sets | 4 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
18 | Lighting & Electrification (Outdoor & Indoor) | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
19 | Steel Supporting Structures of Equipment | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
20 | Fire Fighting Equipment | China | Set | 6 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
21 | LV MCCB Pane | China | Nos. | 2 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
22 | Substation Automation system | EU | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
23 | LED TV, Laptop, Scanner, Printer, LED Electronic Sign Board, Furniture for control room Elivator | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
24 | Recommended Spare parts for GIS Substation | EU | L.S | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
25 | Isolator (11kV, Outdoor Type) | EU | Set | 12 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
26 | Balance of the system |  | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
Civil Works
27 | Land Development with Filling by Sand. | BD | m³ | 3000 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
28 | Sub-Station Buliding | BD | Sq.m. | 1400 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
29 | Transformer Room | BD |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
30 | Switchgear Room | BD |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
31 | Control Room | BD |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
32 | Office Room | BD |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
33 | Boundary Wall / Retain wall | BD | Rm | 275 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
34 | Sub-Station Entrance Gate | BD |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
35 | Guard post | BD |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
36 | Drainage System | BD |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
37 | Inside Road, Approach Road, Walkway | BD | Rm | 138 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
38 | Leveling, Landscaping, Tree plantation, Gardening and beautification etc | BD | LS | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
39 | Yard lighting and emergency lighting | BD | LS | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
40 | Installation including Testing, commissioning | China | Set | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
41 | Inspection & Traning | China |  |  | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
42 | Electrical Drawing | China | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
43 | Civil Drawing | BD | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
44 | Balance of the system | BD | Lot | 1 | 100% | 10% | 5% | 5% | 10% | 50% | 15% | 5%
Total Weight of the Logistics Work |  |  |  |  | 100%

## Construction
Sl.No. | Description of Item | Country of Origin | Unit of Measur ement | Quantity | Weight of the work (%) | Construction
Equipment Supply | [5 empty] | Call for Price proposal from Subcontractor | Collect Price proposal from Subcontractor | Signe Agreement with Subcontractor | Land Excavation for Foundation | Foundation Casting | Foundation Base Casting | Great Beam Casting | Ground Floor Roof Casting | First Floor Roof Casting | Second Floor Roof Casting | Third Floor Roof Casting | Brick Wall Work | Internal Electrical System | Internal Water System | Window Frame | Door Frame | Floor Finishing | Plaster | Electrical System Fittings | Water System Fittings | Window Glass | Door | Stone Procurement | Brick Procurement | Cement Procurement | Iron-Bar Procurement | Sand Procurement | Miscellanies | Remarks
1 | 33kV GIS | EU | Set | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
2 | 11kV GIS | EU | Set | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
3 | Power Transformer (33/11 kV, 20/26 MVA) | China | Nos | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
4 | Station Transformer (33/0.4 kV, 200 kVA) | China | Nos | 2 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
5 | AC Distribution Panel | China | Set | 2 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
6 | DC Distribution Panel | China | Set | 2 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
7 | Battery and Battery Charger (110V) | China | Set | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
8 | XLPE Cable (33kV, 1x500sq.mm) | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
9 | XLPE Cable (11kV, 2x500sq.mm) and (2x120sq.mm) | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
10 | XLPE Cable (11kV, 3Cx95sq.mm) | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
11 | XLPE Cable (11kV, 3Cx185sq.mm) | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
12 | Cable Termination (33kV, 11kV, 0.415kV) | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
13 | Control Cable and LV Power Cables | China | Sets | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
14 | Groundingas Materials Including Cable/Conductor | China | Sets | 12 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
15 | Surge Arrester (Station type 33 kV) | China | Sets | 4 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
16 | Surge Arrester (Station type 11 kV) | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
17 | Air Conditioner of 48,000 BTU Split Type and Exhaust Fan | China | Sets | 4 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
18 | Lighting & Electrification (Outdoor & Indoor) | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
19 | Steel Supporting Structures of Equipment | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
20 | Fire Fighting Equipment | China | Set | 6 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
21 | LV MCCB Pane | China | Nos. | 2 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
22 | Substation Automation system | EU | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
23 | LED TV, Laptop, Scanner, Printer, LED Electronic Sign Board, Furniture for control room Elivator | China | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
24 | Recommended Spare parts for GIS Substation | EU | L.S | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
25 | Isolator (11kV, Outdoor Type) | EU | Set | 12 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
26 | Balance of the system |  | Lot | 1 | 100% | 2% | 3% | 5% | 10% | 60% | 20%
Civil Works
27 | Land Development with Filling by Sand. | BD | m³ | 3000 | 100% | 10% | 10% | 15% | [23 empty] | 65%
28 | Sub-Station Buliding | BD | Sq.m. | 1400 | 100% | 1% | 1% | 2% | 3% | 9% | 6% | 3% | 8% | 8% | 8% | 8% | 7% | 2% | 2% | 2% | 2% | 6% | 4% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2%
29 | Transformer Room | BD |  |  | 100% | 1% | 1% | 2% | 3% | 30% | 10% | 12% | 14% |  |  |  | 5% | 2% |  |  |  | 5% | 2% | 2% |  |  | 1% | 2% | 2% | 2% | 2% | 2%
30 | Switchgear Room | BD |  |  | 100% | 1% | 1% | 2% | 3% | 30% | 10% | 12% | 14% |  |  |  | 5% | 2% |  |  |  | 5% | 2% | 2% |  |  | 1% | 2% | 2% | 2% | 2% | 2%
31 | Control Room | BD |  |  | 100% | 1% | 1% | 2% | 3% | 30% | 10% | 12% | 14% |  |  |  | 5% | 2% |  |  |  | 5% | 2% | 2% |  |  | 1% | 2% | 2% | 2% | 2% | 2%
32 | Office Room | BD |  |  | 100% | 1% | 1% | 2% | 3% | 30% | 10% | 12% | 14% |  |  |  | 5% | 2% |  |  |  | 5% | 2% | 2% |  |  | 1% | 2% | 2% | 2% | 2% | 2%
33 | Boundary Wall / Retain wall | BD | Rm | 275 | 100% | 1% | 1% | 2% | 10% | 10% | 26% | 30% | [10 empty] | 10% |  |  |  |  | 2% | 2% | 2% | 2% | 2%
34 | Sub-Station Entrance Gate | BD |  |  | 100% | 1% | 1% | 2% | 10% | 10% | 15% |  | 51% | [14 empty] | 2% | 2% | 2% | 2% | 2%
35 | Guard post | BD |  |  | 100% | 1% | 1% | 2% | 10% | 10% | 13% |  | 20% |  |  |  | 5% | 2% | 2% | 2% | 2% | 5% | 5% | 2% | 2% | 3% | 3% | 2% | 2% | 2% | 2% | 2%
36 | Drainage System | BD |  |  | 100% | 1% | 1% | 2% | 20% |  | 35% | [5 empty] | 31% | [10 empty] | 2% | 2% | 2% | 2% | 2%
37 | Inside Road, Approach Road, Walkway | BD | Rm | 138 | 100% | 1% | 1% | 2% | 15% |  | 25% | [5 empty] | 46% | [10 empty] | 2% | 2% | 2% | 2% | 2%
38 | Leveling, Landscaping, Tree plantation, Gardening and beautification etc | BD | LS | 1 | 100% | 1% | 1% | 2% | 7% | [23 empty] | 89%
39 | Yard lighting and emergency lighting | BD | LS | 1 | 100% | 5% | 5% | 10% | [9 empty] | 40% | [5 empty] | 40%
40 | Installation including Testing, commissioning | China | Set | 1 | 100% | 5% | 5% | 10% | [24 empty] | 80%
41 | Inspection & Traning | China |  |  | 100% | [27 empty] | 100%
42 | Electrical Drawing | China | Lot | 1 | 100% | [27 empty] | 100%
43 | Civil Drawing | BD | Lot | 1 | 100% | [27 empty] | 100%
44 | Balance of the system | BD | Lot | 1 | 100% | [27 empty] | 100%
Total Weight of the Construction Work |  |  |  |  | 100%

## Installation
Sl.No. | Description of Item | Country of Origin | Unit of Measur ement | Quantity | Weight of the work (%) | Installation Testing & Commissioning
Equipment Supply | [5 empty] | Just Started | Quarter Done | Half Done | 3-Quarter Done | Completed | Remarks
1 | 33kV GIS | EU | Set | 1 | 100% | 5% | 20% | 20% | 25% | 30%
2 | 11kV GIS | EU | Set | 1 | 100% | 5% | 20% | 20% | 25% | 30%
3 | Power Transformer (33/11 kV, 20/26 MVA) | China | Nos | 1 | 100% | 5% | 20% | 20% | 25% | 30%
4 | Station Transformer (33/0.4 kV, 200 kVA) | China | Nos | 2 | 100% | 5% | 20% | 20% | 25% | 30%
5 | AC Distribution Panel | China | Set | 2 | 100% | 5% | 20% | 20% | 25% | 30%
6 | DC Distribution Panel | China | Set | 2 | 100% | 5% | 20% | 20% | 25% | 30%
7 | Battery and Battery Charger (110V) | China | Set | 1 | 100% | 5% | 20% | 20% | 25% | 30%
8 | XLPE Cable (33kV, 1x500sq.mm) | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
9 | XLPE Cable (11kV, 2x500sq.mm) and (2x120sq.mm) | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
10 | XLPE Cable (11kV, 3Cx95sq.mm) | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
11 | XLPE Cable (11kV, 3Cx185sq.mm) | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
12 | Cable Termination (33kV, 11kV, 0.415kV) | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
13 | Control Cable and LV Power Cables | China | Sets | 1 | 100% | 5% | 20% | 20% | 25% | 30%
14 | Groundingas Materials Including Cable/Conductor | China | Sets | 12 | 100% | 5% | 20% | 20% | 25% | 30%
15 | Surge Arrester (Station type 33 kV) | China | Sets | 4 | 100% | 5% | 20% | 20% | 25% | 30%
16 | Surge Arrester (Station type 11 kV) | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
17 | Air Conditioner of 48,000 BTU Split Type and Exhaust Fan | China | Sets | 4 | 100% | 5% | 20% | 20% | 25% | 30%
18 | Lighting & Electrification (Outdoor & Indoor) | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
19 | Steel Supporting Structures of Equipment | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
20 | Fire Fighting Equipment | China | Set | 6 | 100% | 5% | 20% | 20% | 25% | 30%
21 | LV MCCB Pane | China | Nos. | 2 | 100% | 5% | 20% | 20% | 25% | 30%
22 | Substation Automation system | EU | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
23 | LED TV, Laptop, Scanner, Printer, LED Electronic Sign Board, Furniture for control room Elivator | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
24 | Recommended Spare parts for GIS Substation | EU | L.S | 1 | 100% | 5% | 20% | 20% | 25% | 30%
25 | Isolator (11kV, Outdoor Type) | EU | Set | 12 | 100% | 5% | 20% | 20% | 25% | 30%
26 | Balance of the system |  | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
Civil Works
27 | Land Development with Filling by Sand. | BD | m³ | 3000 | 100% | 5% | 20% | 20% | 25% | 30%
28 | Sub-Station Buliding | BD | Sq.m. | 1400 | 100% | 5% | 20% | 20% | 25% | 30%
29 | Transformer Room | BD |  |  | 100% | 5% | 20% | 20% | 25% | 30%
30 | Switchgear Room | BD |  |  | 100% | 5% | 20% | 20% | 25% | 30%
31 | Control Room | BD |  |  | 100% | 5% | 20% | 20% | 25% | 30%
32 | Office Room | BD |  |  | 100% | 5% | 20% | 20% | 25% | 30%
33 | Boundary Wall / Retain wall | BD | Rm | 275 | 100% | 5% | 20% | 20% | 25% | 30%
34 | Sub-Station Entrance Gate | BD |  |  | 100% | 5% | 20% | 20% | 25% | 30%
35 | Guard post | BD |  |  | 100% | 5% | 20% | 20% | 25% | 30%
36 | Drainage System | BD |  |  | 100% | 5% | 20% | 20% | 25% | 30%
37 | Inside Road, Approach Road, Walkway | BD | Rm | 138 | 100% | 5% | 20% | 20% | 25% | 30%
38 | Leveling, Landscaping, Tree plantation, Gardening and beautification etc | BD | LS | 1 | 100% | 5% | 20% | 20% | 25% | 30%
39 | Yard lighting and emergency lighting | BD | LS | 1 | 100% | 5% | 20% | 20% | 25% | 30%
40 | Installation including Testing, commissioning | China | Set | 1 | 100% | 5% | 20% | 20% | 25% | 30%
41 | Inspection & Traning | China |  |  | 100% | 5% | 20% | 20% | 25% | 30%
42 | Electrical Drawing | China | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
43 | Civil Drawing | BD | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
44 | Balance of the system | BD | Lot | 1 | 100% | 5% | 20% | 20% | 25% | 30%
Total Weight of the Installation Testing & Commissioning Work |  |  |  |  | 100%

## Finance
Sl.No. | Description of Item | Country of Origin | Unit of Measur ement | Quantity | Weight of the work (%) | Finance
Equipment Supply | [5 empty] | Submit Invoice to PD Office | Forward to Design Department Two | Forward to PD office | Forward to Finance Department BPDB | Submit Payment Documents to Issuing Bank | Payment Received in HEEC's Account | Remarks
1 | 33kV GIS | EU | Set | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
2 | 11kV GIS | EU | Set | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
3 | Power Transformer (33/11 kV, 20/26 MVA) | China | Nos | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
4 | Station Transformer (33/0.4 kV, 200 kVA) | China | Nos | 2 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
5 | AC Distribution Panel | China | Set | 2 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
6 | DC Distribution Panel | China | Set | 2 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
7 | Battery and Battery Charger (110V) | China | Set | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
8 | XLPE Cable (33kV, 1x500sq.mm) | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
9 | XLPE Cable (11kV, 2x500sq.mm) and (2x120sq.mm) | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
10 | XLPE Cable (11kV, 3Cx95sq.mm) | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
11 | XLPE Cable (11kV, 3Cx185sq.mm) | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
12 | Cable Termination (33kV, 11kV, 0.415kV) | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
13 | Control Cable and LV Power Cables | China | Sets | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
14 | Groundingas Materials Including Cable/Conductor | China | Sets | 12 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
15 | Surge Arrester (Station type 33 kV) | China | Sets | 4 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
16 | Surge Arrester (Station type 11 kV) | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
17 | Air Conditioner of 48,000 BTU Split Type and Exhaust Fan | China | Sets | 4 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
18 | Lighting & Electrification (Outdoor & Indoor) | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
19 | Steel Supporting Structures of Equipment | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
20 | Fire Fighting Equipment | China | Set | 6 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
21 | LV MCCB Pane | China | Nos. | 2 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
22 | Substation Automation system | EU | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
23 | LED TV, Laptop, Scanner, Printer, LED Electronic Sign Board, Furniture for control room Elivator | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
24 | Recommended Spare parts for GIS Substation | EU | L.S | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
25 | Isolator (11kV, Outdoor Type) | EU | Set | 12 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
26 | Balance of the system |  | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
Civil Works
27 | Land Development with Filling by Sand. | BD | m³ | 3000 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
28 | Sub-Station Buliding | BD | Sq.m. | 1400 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
29 | Transformer Room | BD |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
30 | Switchgear Room | BD |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
31 | Control Room | BD |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
32 | Office Room | BD |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
33 | Boundary Wall / Retain wall | BD | Rm | 275 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
34 | Sub-Station Entrance Gate | BD |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
35 | Guard post | BD |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
36 | Drainage System | BD |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
37 | Inside Road, Approach Road, Walkway | BD | Rm | 138 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
38 | Leveling, Landscaping, Tree plantation, Gardening and beautification etc | BD | LS | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
39 | Yard lighting and emergency lighting | BD | LS | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
40 | Installation including Testing, commissioning | China | Set | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
41 | Inspection & Traning | China |  |  | 100% | 5% | 5% | 10% | 5% | 40% | 35%
42 | Electrical Drawing | China | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
43 | Civil Drawing | BD | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
44 | Balance of the system | BD | Lot | 1 | 100% | 5% | 5% | 10% | 5% | 40% | 35%
Total Weight of the Finance Work |  |  |  |  | 100%

## Drop Down
Design | Select Option | Submit to PD office | Forward to Design Department Three | Forward to PD office from DD3 | Forward to Design Department Two | Forward to PD office from DD2 | Receive Approved Drawing from PD Office | Handover Approved Drawing to Site Engineer | Remarks
Procurement | Select Option | Call for Offer | Collect Offer | Contract Sign with Supplier | Take out Goods from Manufacturer | Collect Shipping Documents | Handover Shipping Documents to Logistics Department | Remarks
Logistics | Select Option | Submit Shipping Documents to Presenting Bank | Collect Shipping Documents from Issuing Bank | Endorsement Shipping Documents | Submit to Customs Office | Take Out Goods from Port | Send to Site | Handover Shipping Documents to Finance Department | Remarks
Construction | Select Option | Call for Price proposal from Subcontractor | Collect Price proposal from Subcontractor | Sign Agreement with Subcontractor | Land Excavation for Foundation | Foundation Casting | Foundation Base Casting | Great Beam Casting | Ground Floor Roof Casting | First Floor Roof Casting | Second Floor Roof Casting | Third Floor Roof Casting | Brick Wall Work | Internal Electrical System | Internal Water System | Window Frame | Door Frame | Floor Finishing | Plaster | Electrical System Fittings | Water System Fittings | Window Glass | Door | Stone Procurement | Brick Procurement | Cement Procurement | Iron-Bar Procurement | Sand Procurement | Miscellanies | Remarks
Installation | Select Option | Just Started | Quarter Done | Half Done | 3-Quarter Done | Completed | Remarks
Finance | Select Option | Submit Invoice to PD Office | Forward to Design Department Two | Forward to PD office | Forward to Finance Department BPDB | Submit Payment Documents to Issuing Bank | Payment Received in HEEC's Account | Remarks