## Sheet1
SL | Phase | Module | Task | Delivery Status | Completion Day Gradually | Status | Remarks
1 | 1st Phase | Architectural Module | System Analysis | Not Deliverable | 3 | Complete
2 |  |  | Architectural Design | Not Deliverable | 1 | Complete
3 |  |  | Database Design | Deliverable | 2 | Complete
4 |  |  | Layout Design | Deliverable | 2 | Complete
5 |  | System Admin Module | Login Panel | Deliverable | 1 | Complete
6 |  |  | Project Creation | Deliverable | 1 | Incomplete
7 |  |  | Project Listing | Deliverable | 1 | Incomplete
8 |  |  | Project Overview | Deliverable | 2 | Incomplete
9 |  |  | Task, Sub-task, Sub-sub-task Creation | Deliverable |  | Incomplete
10 |  |  | Department Module | Deliverable | 1 | Incomplete
11 |  |  | Status Module | Deliverable |  | Incomplete
12 |  |  | Department - Task Module | Deliverable | 2 | Incomplete
13 |  |  | Assign User Module | Deliverable | 1 | Incomplete
14 |  |  | Edit Project | Deliverable |  | Complete
15 |  |  | User Module | Deliverable | 3 | Incomplete
16 |  |  | Client Module | Deliverable | 1 | Complete
17 |  |  | Contactor Module | Deliverable |  | Complete
18 |  |  | Currency Setup Module | Deliverable |  | Incomplete
19 |  |  | Notification Module | Deliverable | 2 | Incomplete
20 |  | Users Module | Ongoing Project List | Deliverable | 10 | Incomplete
21 |  |  | Expand any project and details of department | Deliverable |  | Incomplete
22 |  |  | Expand any department and details task tree | Deliverable |  | Incomplete
23 |  |  | Expand any task and details of that task or sub task or sub sub task | Deliverable |  | Incomplete
24 |  |  | Sub- Sub task related actionaries | Deliverable |  | Incomplete
25 |  |  | User Profile | Deliverable | 1 | Incomplete
26 |  |  | Completed Project | Deliverable |  | Incomplete
27 | 2nd Phase | Both Module task are there | Forgot Password and reset password. | Deliverable | 1 | Incomplete
28 |  |  | Chart for the deviation between actual progress and scheduled progress of the project | Deliverable | 1 | Incomplete
29 |  |  | Remarks input and edit | Deliverable | 1 | Incomplete
30 |  |  | Files upload, request for delete or modification. | Deliverable | 1 | Incomplete
31 |  |  | Make a project as completed | Deliverable |  | Incomplete
32 |  |  | Make an incomplete project as completed. | Deliverable |  | Incomplete
33 |  |  | Critical task list | Deliverable |  | Incomplete
34 |  |  | User list with details | Deliverable | 1 | Incomplete
35 |  |  | Media | Deliverable |  | Incomplete
36 |  |  | Import a new project from excel. | Deliverable | 1 | Incomplete
37 |  |  | Drag and drop of list. | Deliverable |  | Incomplete
38 |  |  | Multi-selection of task. | Deliverable | 1 | Incomplete
39 |  |  | Edit task | Deliverable |  | Incomplete
40 |  |  | System Log Module | Deliverable | 1 | Incomplete
41 |  |  | System Settings | Deliverable |  | Incomplete
42 |  |  | Report Generation. | Deliverable | 4 | Incomplete
43 |  |  | Cloning of a project. | Deliverable | 1 | Incomplete
44 |  |  | Export Projects. | Deliverable |  | Incomplete
|  |  |  | Total (Days) | 47
1st Phase Need to complete within 28-01-2019
2nd Phase Need to complete within 22-02-2019